## Sheet1
Dave Sullivan -Enterprise Java, Individaul Project Plan
Objective | Week
Application to establish a weekly tennis league. Initially, a single league, a set of players, establish dates, court and player assignments. Desired functionality to include player entry, league setup, determination of dates for court/player assignment. Additional functionality might be recording score, confirming email (via webservice), updated schedule with weekly standings, multiple league types, dynamically determining #courts, #dates based on player count parameters to establish a new league. | 2015-09-28
Hardcode single set of players, league, dates, page layout. | 2015-10-05
Research the permutations logic to establish combinations business logic. | 2015-10-19
Create player and database elements. | 2015-10-26
Create league based on players, courts, dates. | 2015-11-02
Output a league/player assignment of courts and dates. | 2015-11-16
Establish security for player entry vs league admin pages. | 2015-11-30
Expanded enhancements; might be a date picker, alternating line highlights, ability to email the schedule, email validation. Probably some type of JQuery or AJAX based functionality to the base application, depending on time available for enhanncements. | 2015-12-07
Present project | 2015-12-21